## Plan de charge QA DH
| Plan de Charge - QA DH |  | 2025 | [12 empty] | DH Patch Release |  |  |  |  | DH Minor Release |  |  |  |  | Sprint Automation
[9 empty] | SP 101 |  | SP 102 |  | SP 103 |  | SP 104 |  | SP 105 |  | SP 106 |  | SP 107 |  | SP 108 |  | SP 109 |  | SP 110 |  | SP 111 |  | SP 112 |  | SP 113 |  | SP 114 |  | SP 115 |  | SP 116 |  | SP 117 |  | SP 118 |  | SP 119 |  | SP 120 |  | SP 121 |  | SP 122 |  | SP 123 |  | SP 124 |  | SP 125
[15 empty] | DH-7.3.3.0 |  | DH-7.3.3.0 / DH-7.5.2.0 | DH-7.5.2.0
Topic | Task | Test Start Date | QA | Team | Estimé | planifié | Ecart | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28
[8 empty] | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
DH Releases | Regression Tests & retrofits |  | Abir Arrari | Delivery |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Molka Gmar | Delivery |  | 13 | -13 | S9: 4; S10: 2; S11: 3; S12: 4
DH Releases | Regression Tests & retrofits |  | Asma Korbi | Roadmap |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Ferdews Tlili | Delivery |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Ikram Dhraief | Delivery |  | 5.5 | -5.5 | S9: 3.5; S11: 2
DH Releases | Regression Tests & retrofits |  | Imen Ben Bechir | Delivery |  | 1 | -1 | bar: S9
DH Releases | Regression Tests & retrofits |  | Wieme Abidi | Delivery |  | 13 | -13 | S9: 4; S10: 4; S12: 5
DH Releases | Regression Tests & retrofits |  | Yassine Sboui | Delivery |  | 10 | -10 | S9: 4; S10: 2; S12: 4
DH Releases | Regression Tests & retrofits |  | Ala Eddine Boukhris | Cloud |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Manel Chaabene | Cloud |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Oussama Ouledabdallah | Cloud |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Wafa Kallel | Roadmap |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Islem Louati | Roadmap |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Rehab Ezzine | Roadmap |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Imen Habaieb | Roadmap |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Maroua Aissa | Roadmap |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Houssem Ousji | Automation |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Wassim Malouch | Automation |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Manel Bacha | Automation |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Monia Dkhil | Automation |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Nesrine Dhaouadi | Automation |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Ramy Chaaleb | Automation |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Safa Ezzaouia | Automation |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Sarra Ben Guerga | Automation |  | 0 | 0
DH Releases | Regression Tests & retrofits |  | Takwa Jaouadi | Automation |  | 0 | 0
DH Releases | Automated tests suites Analysis |  | Manel Bacha | Automation |  | 0 | 0
DH Releases | Automated tests suites Analysis |  | Monia Dkhil | Automation |  | 0 | 0
DH Releases | Automated tests suites Analysis |  | Nesrine Dhaouadi | Automation |  | 0 | 0
DH Releases | Automated tests suites Analysis |  | Ramy Chaaleb | Automation |  | 0 | 0
DH Releases | Automated tests suites Analysis |  | Safa Ezzaouia | Automation |  | 0 | 0
DH Releases | Automated tests suites Analysis |  | Sarra Ben Guerga | Automation |  | 0 | 0
DH Releases | Automated tests suites Analysis |  | Takwa Jaouadi | Automation |  | 0 | 0
DH Releases | Automated tests suites Analysis |  | Houssem Ousji | Automation |  | 0 | 0
DH Releases | Automated tests suites Analysis |  | Wassim Malouch | Automation |  | 0 | 0
Maintenance | Continious testing - Retrofits |  | Abir Arrari | Delivery |  | 0 | 0
Maintenance | Regression Tests for QF |  | Abir Arrari | Delivery |  | 0 | 0
Maintenance | GIC Improvment |  | Abir Arrari | Delivery |  | 0 | 0
Roadmap | Refonte IBOR |  | Abir Arrari | Delivery |  |  | 0
Maintenance | Regression tests reformulation |  | Abir Arrari | Delivery |  | 0 | 0
Maintenance | Continious testing - Retrofits |  | Molka Gmar | Delivery |  | 0 | 0
Maintenance | Regression Tests for QF |  | Molka Gmar | Delivery |  | 3 | -3 | S9: 1; S10: 2
Maintenance | Regression tests reformulation |  | Molka Gmar | Delivery |  | 0
Maintenance | Continious testing - Retrofits |  | Ikram Dhraief | Delivery |  | 0 | 0
Roadmap | RTO |  | Ikram Dhraief | Delivery
Maintenance | Regression Tests for QF |  | Ikram Dhraief | Delivery |  | 13 | -13 | S9: 1; S10: 5; S11: 3; S12: 4
Maintenance | Regression tests reformulation |  | Ikram Dhraief | Delivery |  | 0
Maintenance | Continious testing - Retrofits |  | Imen Ben Bechir | Delivery |  | 0 | 0
Maintenance | Regression Tests for QF |  | Imen Ben Bechir | Delivery |  | 0 | 0
Maintenance | GIC Improvment |  | Imen Ben Bechir | Delivery |  | 0 | 0
Maintenance | Regression tests reformulation |  | Imen Ben Bechir | Delivery |  | 0
Maintenance | Continious testing - Retrofits |  | Wieme Abidi | Delivery |  | 0 | 0
Maintenance | Regression Tests for QF |  | Wieme Abidi | Delivery |  | 0 | 0
Maintenance | GIC Improvment |  | Wieme Abidi | Delivery | 7 | 0 | 7
Roadmap | Release Management.with.GIT |  | Wieme Abidi | Delivery |  | 0 | 0
Maintenance | Regression tests reformulation |  | Wieme Abidi | Delivery |  | 0
Maintenance | Continious testing - Retrofits |  | Yassine Sboui | Delivery |  | 0 | 0
Maintenance | Regression Tests for QF |  | Yassine Sboui | Delivery |  | 2 | -2 | S10: 2
Maintenance | Regression tests reformulation |  | Yassine Sboui | Delivery |  | 0
Maintenance | Continious testing - Retrofits |  | Ferdews Tlili | Delivery |  | 0 | 0
Maintenance | Regression Tests for QF |  | Ferdews Tlili | Delivery |  | 0 | 0
Maintenance | Retrofits 7.2 |  | Abir Arrari | Delivery |  | 0 | 0
Maintenance | Retrofits 7.2 |  | Molka Gmar | Delivery |  | 0 | 0
Maintenance | Pictet Test Plan |  | Ikram Dhraief | Delivery |  | 0 | 0
Maintenance | Pictet Test Plan |  | Imen Ben Bechir | Delivery |  | 13 | -13 | S9: 4; S10: 5; S11: 4
Maintenance | Retrofits 7.2 |  | Wieme Abidi | Delivery |  | 0 | 0
Maintenance | Retrofits 7.2 |  | Yassine Sboui | Delivery |  | 0 | 0
Maintenance | Tickets VULN |  | Safa Ezzaouia | Automation |  | 0 | 0
Data@ccess | UC1 - Analysis & test design |  | Asma Korbi | Roadmap |  | 0 | 0
Data@ccess | UC1 - Test Execution |  | Asma Korbi | Roadmap |  | 0 | 0
Data@ccess | UC1 - Analysis & test design |  | Sarra Ben Guerga | Automation |  | 0 | 0
Data@ccess | UC1 - Test Execution |  | Sarra Ben Guerga | Automation |  | 0 | 0
Data@ccess | Design & Suivi |  | Maroua Aissa | Roadmap |  | 0 | 0
Automation | Gestion backlog |  | Maroua Aissa | Roadmap |  | 0 | 0
Automation | New implementation |  | Houssem Ousji | Automation |  | 0 | 0
Automation | Maintenance |  | Houssem Ousji | Automation |  | 0 | 0
Automation | Analyse (Continuous) |  | Houssem Ousji | Automation |  | 0 | 0
Automation | New implementation |  | Manel Bacha | Automation |  | 0 | 0
Automation | Maintenance |  | Manel Bacha | Automation |  | 0 | 0
Automation | Analyse (Continuous) |  | Manel Bacha | Automation |  | 0 | 0
Automation | New implementation |  | Monia Dkhil | Automation |  | 0 | 0
Automation | Maintenance |  | Monia Dkhil | Automation |  | 0 | 0
Automation | Analyse (Continuous) |  | Monia Dkhil | Automation |  | 0 | 0
Automation | New implementation |  | Nesrine Dhaouadi | Automation |  | 0 | 0
Automation | Maintenance |  | Nesrine Dhaouadi | Automation |  | 0 | 0
Automation | Analyse (Continuous) |  | Nesrine Dhaouadi | Automation |  | 0 | 0
Automation | New implementation |  | Ramy Chaaleb | Automation |  | 0 | 0
Automation | Maintenance |  | Ramy Chaaleb | Automation |  | 0 | 0
Automation | Analyse (Continuous) |  | Ramy Chaaleb | Automation |  | 0 | 0
Automation | New implementation |  | Safa Ezzaouia | Automation |  | 0 | 0
Automation | Maintenance |  | Safa Ezzaouia | Automation |  | 0 | 0
Automation | Analyse (Continuous) |  | Safa Ezzaouia | Automation |  | 0 | 0
Automation | New implementation |  | Sarra Ben Guerga | Automation |  | 0 | 0
Automation | Maintenance |  | Sarra Ben Guerga | Automation |  | 0 | 0
Automation | Analyse (Continuous) |  | Sarra Ben Guerga | Automation |  | 0 | 0
Automation | New implementation |  | Takwa Jaouadi | Automation |  | 0 | 0
Automation | Maintenance |  | Takwa Jaouadi | Automation |  | 0 | 0
Automation | Analyse (Continuous) |  | Takwa Jaouadi | Automation |  | 0 | 0
Automation | New implementation |  | Wassim Malouch | Automation |  | 0 | 0
Automation | Maintenance |  | Wassim Malouch | Automation |  | 0 | 0
Automation | Analyse (Continuous) |  | Wassim Malouch | Automation |  | 0 | 0
Cloud | Retrofits 7.2 |  | Ala Eddine Boukhris | Cloud |  | 0 | 0
Cloud | Retrofits 7.2 |  | Oussama Ouledabdallah | Cloud |  | 0 | 0
Cloud | Retrofits 7.2 |  | Manel Chaabene | Cloud |  | 0 | 0
Cloud | Regression tests coverage |  | Ala Eddine Boukhris | Cloud |  | 0 | 0
Cloud | Regression tests coverage |  | Manel Chaabene | Cloud |  | 0 | 0
Cloud | Regression tests coverage |  | Oussama Ouledabdallah | Cloud |  | 0 | 0
Cloud | keycloak - Aws et Azure |  | Ala Eddine Boukhris | Cloud |  | 0 | 0
Cloud | keycloak - Aws et Azure |  | Manel Chaabene | Cloud |  | 0 | 0
Cloud | keycloak - Aws et Azure |  | Oussama Ouledabdallah | Cloud |  | 0 | 0
Cloud | Openshift |  | Ala Eddine Boukhris | Cloud |  | 0 | 0
Cloud | Openshift |  | Manel Chaabene | Cloud |  | 0 | 0
Cloud | Openshift |  | Oussama Ouledabdallah | Cloud |  | 0 | 0
Cloud | Continious testing - Retrofits |  | Ala Eddine Boukhris | Cloud |  | 0 | 0
Cloud | Continious testing - Retrofits |  | Manel Chaabene | Cloud |  | 0 | 0
Cloud | Continious testing - Retrofits |  | Oussama Ouledabdallah | Cloud |  | 0 | 0
Cloud | QA Improvments |  | Ala Eddine Boukhris | Cloud |  | 0 | 0
Cloud | QA Improvments |  | Manel Chaabene | Cloud |  | 0 | 0
Cloud | QA Improvments |  | Oussama Ouledabdallah | Cloud |  | 0 | 0
Roadmap | Visage |  | Islem Louati | Roadmap |  | 0 | 0
Roadmap | Visage |  | Imen Habaieb | Roadmap |  | 0 | 0
Roadmap | Visage |  | Rehab Ezzine | Roadmap |  | 0 | 0
Roadmap | Visage |  | Monia Dkhil | Automation |  | 0 | 0
Roadmap | Retrofits 7.2 |  | Islem Louati | Roadmap |  | 0 | 0
Roadmap | Retrofits 7.2 |  | Imen Habaieb | Roadmap |  | 0 | 0
Roadmap | Retrofits 7.2 |  | Rehab Ezzine | Roadmap |  | 0 | 0
Roadmap | Retrofits 7.2 |  | Wafa Kallel | Roadmap |  | 0 | 0
Roadmap | DataManagement.Capitol.DQC.NewDataModel |  | Wafa Kallel | Roadmap |  | 0 | 0
Roadmap | DataManagement.DQL.Productization |  | Wafa Kallel | Roadmap |  | 0 | 0
Roadmap | DataManagement.ManualOverride.Lot1.Improvement |  | Wafa Kallel | Roadmap |  | 0 | 0
Roadmap | DataManagement.ManualOverride.Lot2.Improvement |  | Wafa Kallel | Roadmap |  | 0 | 0
Roadmap | DataManagement.Bitemporal.Stabilization |  | Imen Matoussi |  |  | 0 | 0
Roadmap | DataManagement.Capitol.DQC.NewDataModel.UserInterface |  |  |  |  | 0 | 0
Roadmap | DataManagement.ManualOverride.Lot1.FrontToBack |  | Islem Louati | Roadmap |  | 0 | 0
Roadmap | DataManagement.ManualOverride.Lot2.FrontToBack |  | Islem Louati | Roadmap |  | 0 | 0
Roadmap | FederatedTenant.AccountStructure.Front.Integration |  | Rehab Ezzine | Roadmap |  | 0 | 0
Roadmap | FederatedTenant.API.scopeDef |  | Sarra Ben Guerga | Automation |  | 0 | 0
Roadmap | FederatedTenant.MonitoringConsole |  | Islem Louati | Roadmap |  | 0 | 0
Roadmap | FederatedTenant.ServiceCard |  | Asma Korbi | Roadmap |  | 0 | 0
Roadmap | FederatedTenant.SSO |  | Islem Louati | Roadmap |  | 0 | 0
Roadmap | FederatedTenant.UI.Switch |  | Islem Louati | Roadmap |  | 0 | 0
Roadmap | Release Management.with.GIT |  | Ferdews Tlili | Delivery |  | 0 | 0
Management | Suivi & Managment de l'activité |  | Ferdews Tlili | Delivery
Management | Suivi & Managment de l'activité |  | Maroua Aissa | Roadmap
Management | Suivi & Managment de l'activité |  | Nesrine Dhaouadi | Automation
Management | Suivi & Managment de l'activité |  | Manel Chaabene | Cloud |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Ikram Dhraief | Delivery |  | 2.5 |  | S9: 0.5; S11: 1; S12: 1
Absence | Absence (CP, Maladie, Férié etc.) |  | Imen Ben Bechir | Delivery |  | 11 |  | S11: 1; S12: 5; S13: 5
Absence | Absence (CP, Maladie, Férié etc.) |  | Wieme Abidi | Delivery |  | 7 |  | S9: 1; S10: 1; S11: 5
Absence | Absence (CP, Maladie, Férié etc.) |  | Yassine Sboui | Delivery |  | 4 |  | S11: 4
Absence | Absence (CP, Maladie, Férié etc.) |  | Ferdews Tlili | Delivery |  | 1 | bar: S11
Absence | Absence (CP, Maladie, Férié etc.) |  | Molka Gmar | Delivery |  | 1 | bar: S11
Absence | Absence (CP, Maladie, Férié etc.) |  | Abir Arrari | Delivery |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Ala Eddine Boukhris | Cloud |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Manel Chaabene | Cloud |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Oussama Ouledabdallah | Cloud |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Wafa Kallel | Roadmap |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Asma Korbi | Roadmap
Absence | Absence (CP, Maladie, Férié etc.) |  | Islem Louati | Roadmap |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Rehab Ezzine | Roadmap |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Imen Habaieb | Roadmap |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Maroua Aissa | Roadmap |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Houssem Ousji | Automation |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Wassim Malouch | Automation |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Manel Bacha | Automation |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Monia Dkhil | Automation |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Nesrine Dhaouadi | Automation |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Ramy Chaaleb | Automation |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Safa Ezzaouia | Automation |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Sarra Ben Guerga | Automation |  | 0
Absence | Absence (CP, Maladie, Férié etc.) |  | Takwa Jaouadi | Automation |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Abir Arrari | Delivery |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Molka Gmar | Delivery |  | 3 | bar: S10 to S12
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Asma Korbi | Roadmap |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Ferdews Tlili | Delivery |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Ikram Dhraief | Delivery |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Imen Ben Bechir | Delivery |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Wieme Abidi | Delivery |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Yassine Sboui | Delivery |  | 52 | bar: S1 to S52
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Ala Eddine Boukhris | Cloud |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Manel Chaabene | Cloud |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Oussama Ouledabdallah | Cloud |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Wafa Kallel | Roadmap |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Islem Louati | Roadmap |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Rehab Ezzine | Roadmap |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Imen Habaieb | Roadmap |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Maroua Aissa | Roadmap |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Houssem Ousji | Automation |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Wassim Malouch | Automation |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Manel Bacha | Automation |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Monia Dkhil | Automation |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Nesrine Dhaouadi | Automation |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Ramy Chaaleb | Automation |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Safa Ezzaouia | Automation |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Sarra Ben Guerga | Automation |  | 0
Formation | Formation (onboarding, interne, externe, Etudes universitaires etc.) |  | Takwa Jaouadi | Automation |  | 0
Total |  | DH Releases | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16.5 | 8 | 5 | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | Maintenance | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 14 | 7 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | Data@ccess | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | Automation | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | Cloud | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | Roadmap | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total planifié |  | Management | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total planifié |  | QA DH | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 22.5 | 22 | 12 | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Nombre de ressources | [5 empty] | 23 | 23 | 23 | 23 | 23 | 23 | 23 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
Total |  | Capacité Brute | [5 empty] | 115 | 115 | 115 | 115 | 115 | 115 | 115 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125 | 125
Total |  | Absence | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  | Formation | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Total |  | Capacité prod Max | [5 empty] | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 124 | 124 | 123 | 123 | 123 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124
Total |  | Ecart | [5 empty] | 114 | 114 | 114 | 114 | 114 | 114 | 114 | 124 | 101.5 | 101 | 111 | 106 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124 | 124
| FTE PROD | Delivery | 7
| FTE PROD | Cloud | 3
| FTE PROD | Automation | 9
| FTE PROD | Roadmap | 6
| Total planifié | Delivery | [5 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 25 | 25 | 27 | 25 | 6 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Ecart | Delivery | [5 empty] | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 10 | 10 | 8 | 10 | 29 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34 | 34
| Total planifié | Cloud | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ecart | Cloud | [5 empty] | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
| Total planifié | Automation | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ecart | Automation | [5 empty] | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45 | 45
| Total planifié | Roadmap | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Ecart | Roadmap | [5 empty] | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30
Note on R7: Ferdews Tlili: DH-7.5.2.0
Note on R13: Ferdews Tlili: DH-7.5.2.0
Note on Q46: Ferdews Tlili: Amundi DH-6.2-02c-qf12b9
Note on R46: Ferdews Tlili: Amundi DH-6.2-02c-qf12b9
Note on Q50: Ferdews Tlili: DH-6.6.3.6 QF
Note on R50: Ferdews Tlili: QF DH-6.6.3.6 QF Amundi DH-6.2-02c-qf12b9
Note on R62: Ferdews Tlili: QF DH-6.6.3.6

## PDC MTC
|  | Plan de Charge - QA MTC |  |  |  | 2026 | [14 empty] | QF |  | Patch Release |  | Minor Release | [7 empty] | Ticket | TNR
[23 empty] | DH-7.6.0-0 | [9 empty] | 0.5 | 0.25
Dh-7.4.2-0
[18 empty] | DH-7.3.3.0 |  | DH-7.3.3.0 / DH-7.5.2.0 | DH-7.5.2.0 |  | DH-6.3-03-qf2b8 | DH-7.2.3.4 | DH-7.3.3.1/ DH-7.5.2-1
Topic | Version | Customer | Code Freeze Date | Delivery Date | Tickets Number | TNR | Status | Estimé | planifié | Ecart | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01
[11 empty] | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22
Releases | DH-7.3.3.0 | nomura-clients ubs-clients | 2026-02-18 | 2026-03-16 |  |  | In TEST | 0 | 0 | 0
Releases | DH-6.6.3.6 | guardian-life-clients cnp-clients | 2026-03-05 | 2026-03-11 | 7 | 10 | In DEV | 6 | 4 | -2 | S9: 1; S10: 3
Releases | DH-6.2-02c-qf12b9 | amundi-clients | 2026-03-05 | 2026-03-13 | 4 | 6 | In TEST | 3.5 | 2 | -1.5 | S10: 2
Releases | DH-7.5.2-0 | GIC | 2026-03-11 | 2026-03-25 | 32 | 55 | In DEV | 29.75 | 20 | -9.75 | S10: 6; S11: 5; S12: 9
Releases | DH-7.4.2.0 | fbn-clients / zkb-clients / bnp-clients | ?? | ?? |  |  | In DEV | 0 | 0 | 0
Releases | DH-7.4.1.3 | zkb-clients euroclear-clients | 2026-03-09 | 18/03/2026 (à confirmer) | 7 | 15 | In DEV | 7.25 | 0 | -7.25
Releases | DH-6.3-03-qf2b8 | lodier-clients |  | 2026-04-03 |  |  | In TEST | 0 | 0 | 0
Releases | DH-7.2.3.4 | GIC | 2026-04-02 | 2026-04-08 | 4 |  | In DEV | 2 | 0 | -2
Releases | DH-7.3.3.1 | Pictet Group/ Nomura | 2026-04-03 | 2026-04-15 | 16 |  | In DEV | 8 | 0 | -8
Releases | DH-7.5.2-1 | GIC | 2026-04-03 | 2026-04-23 | 21 |  | In DEV | 10.5 | 0 | -10.5
Releases | DH-7.4.2-0 | BNP/FBN | 2026-04-10 | 2026-04-30 | 82 |  | In DEV | 41 | 0 | -41
Releases | DH-7.6.0-0 | neoxam | 2026-04-01 | 2026-04-29 | 208 |  | Ready to TEST | 104 | 0 | -104
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [8 empty] | 0
Maintenance | [7 empty] | 0 | 0 | 0
Roadmap | [7 empty] | 0 | 0 | 0
Maintenance | [7 empty] | 0 | 0 | 0
Maintenance | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [7 empty] | 0 | 0 | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Maintenance | [8 empty] | 0
Maintenance | [8 empty] | 0
Maintenance | Zero Vuln |  |  |  | 2 |  |  |  | 0
Maintenance | GIC Improvments | [6 empty] | 29 | 0 | -29
Roadmap | Release Management.with.GIT | [6 empty] | 31 | 0 | -31
Roadmap | Refonte IBOR | [7 empty] | 0
Roadmap | West PAC - RTO | [7 empty] | 0
Maintenance | Tickets 4-eyes BNP |  | 2025-11-05 | [5 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Releases | [8 empty] | 0
Absence |  | (CP, Maladie, Férié etc.) |  |  |  | Ikram Dhraief |  |  | 0
Absence |  | (CP, Maladie, Férié etc.) |  |  |  | Imen Ben Bechir |  |  | 0
Absence |  | (CP, Maladie, Férié etc.) |  |  |  | Wieme Abidi |  |  | 0
Absence |  | (CP, Maladie, Férié etc.) |  |  |  | Yassine Sboui |  |  | 0
Absence |  | (CP, Maladie, Férié etc.) |  |  |  | Amani Ben Arbia |  |  | 0
Absence |  | (CP, Maladie, Férié etc.) |  |  |  | Abir Arrari |  |  | 0
Formation |  | Formation & Etudes |  |  |  | Abir Arrari |  |  | 0
Formation |  | Formation & Etudes |  |  |  | Amani Ben Arbia |  |  | 0
Formation |  | Formation & Etudes |  |  |  | Ikram Dhraief |  |  | 0
Formation |  | Formation & Etudes |  |  |  | Imen Ben Bechir |  |  | 0
Formation |  | Formation & Etudes |  |  |  | Wieme Abidi |  |  | 0
Formation |  | Formation & Etudes |  |  |  | Yassine Sboui |  |  | 0
Total |  |  |  |  | Releases
Total |  |  |  |  | Maintenance
Total |  |  |  |  | Roadmap
TOTAL
[5 empty] | Nombre de ressources | Delivery
Total |  |  |  |  | Capacité Brute
Total |  |  |  |  | Absence
Total |  |  |  |  | Formation
Total |  |  |  |  | Capacité prod Max
Total |  |  |  |  | Ecart
Formulas:
QF = [DH-7.3.3.0 / DH-7.5.2.0]+7
DH-7.2.3.4 = [Patch Release]+7
Minor Release = [DH-7.2.3.4]+7
Note on F10: Ferdews Tlili: Total: 79 Maintenance: 32: 12 fixed: 4 GIC Roadmap: 19
Note on F12: Ferdews Tlili: 12 - 1 (ticket resolved bys configuration) 7 tickets To be tested: 3 tickets ZKB + 4 tickets Vuln
Note on I42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 13 JH à partir de la semaine 17/03 16 JH à partir de la semaine 24/03
Note on I54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 29 JH à partir de la semaine 17/03
Note on I55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 24 JH à partir de la semaine 17/03

## CAPA QA DH
Ressource | Capacité | PROD | MNGT | Team | Ressource | Capacité | PROD | MNGT | Ressource | Capacité | PROD | MNGT
Abir Arrari | 100% | 100% | 0% | Roadmap | Abir Arrari | 100% | 100% | 0% | Houssem Ousji | 100% | 100% | 0%
Ala Eddine Boukhris | 100% | 100% | 0% | Cloud | Molka Gmar | 100% | 100% | 0% | Manel Bacha | 100% | 100% | 0%
Amani Ben Arbia | 100% | 100% | 0% | Delivery | Ferdews Tlili | 100% | 30% | 70% | Monia Dkhil | 100% | 100% | 0%
Asma Korbi | 100% | 100% | 0% | Roadmap | Ikram Dhraief | 100% | 100% | 0% | Nesrine Dhaouadi | 100% | 50% | 50%
Ferdews Tlili | 100% | 30% | 70% |  | Imen Ben Bechir | 100% | 100% | 0% | Ramy Chaaleb | 100% | 100% | 0%
Houssem Ousji | 100% | 100% | 0% | Automation | Wieme Abidi | 100% | 100% | 0% | Safa Ezzaouia | 100% | 100% | 0%
Ikram Dhraief | 100% | 100% | 0% | Delivery | Yassine Sboui | 100% | 100% | 0% | Sarra Ben Guerga | 100% | 100% | 0%
Imen Ben Bechir | 100% | 100% | 0% | Delivery | Total FTE | 7 | 6.3 | 0.7 | Takwa Jaouadi | 100% | 100% | 0%
Imen Habaieb | 100% | 100% | 0% | Roadmap |  |  |  |  | Wassim Malouch | 100% | 100% | 0%
Islem Louati | 100% | 100% | 0% | Roadmap |  |  |  |  | Total FTE | 9 | 8.5 | 0.5
Manel Bacha | 100% | 100% | 0% | Automation | Ressource | Capacité | PROD | MNGT
Manel Chaabene | 100% | 70% | 30% | Cloud | Asma Korbi | 100% | 100% | 0%
Maroua Aissa | 100% | 50% | 50% | Roadmap | Imen Habaieb | 100% | 100% | 0%
Monia Dkhil | 100% | 100% | 0% | Automation | Islem Louati | 100% | 100% | 0%
Nesrine Dhaouadi | 100% | 50% | 50% | Automation | Maroua Aissa | 100% | 60% | 40%
Oussama Ouledabdallah | 100% | 100% | 0% | Cloud | Rehab Ezzine | 100% | 100% | 0%
Ramy Chaaleb | 100% | 100% | 0% | Automation | Wafa Kallel | 100% | 100% | 0%
Rehab Ezzine | 100% | 100% | 0% | Roadmap | Total FTE | 6 | 5.6 | 0.4
Safa Ezzaouia | 100% | 100% | 0% | Automation
Sarra Ben Guerga | 100% | 100% | 0% | Automation | Ressource | Capacité | PROD | MNGT
Takwa Jaouadi | 100% | 100% | 0% | Automation | Ala Eddine Boukhris | 100% | 100% | 0%
Wafa Kallel | 100% | 100% | 0% | Roadmap | Manel Chaabene | 100% | 70% | 30%
Wassim Malouch | 100% | 100% | 0% | Automation | Oussama Ouledabdallah | 100% | 100% | 0%
Wieme Abidi | 100% | 100% | 0% | Delivery | Total FTE | 3 | 2.7 | 0.3
Yassine Sboui | 100% | 100% | 0% | Delivery
Total FTE | 25 | 23 | 2

## CAPA QA DH OLD (hidden)
| 2024-01-01 | [5 empty] | 2024-01-08 | [5 empty] | 2024-01-15 | [5 empty] | 2024-01-22 | [5 empty] | 2024-01-29 | [5 empty] | 2024-02-05 | [5 empty] | 2024-02-12 | [5 empty] | 2024-02-19 | [5 empty] | 2024-02-26 | [5 empty] | 2024-03-04 | [5 empty] | 2024-03-11 | [5 empty] | 2024-03-18 | [5 empty] | 2024-03-25
Ressource | S1 | [5 empty] | S2 | [5 empty] | S3 | [5 empty] | S4 | [5 empty] | S5 | [5 empty] | S6 | [5 empty] | S7 | [5 empty] | S8 | [5 empty] | S9 | [5 empty] | S10 | [5 empty] | S11 | [5 empty] | S12 | [5 empty] | S13
| Capacité E | MAINT | R&D | QAaaS | AUTO | MNGT | Capacité T | MAINT | R&D | QAaaS | AUTO | MNGT | Capacité T | MAINT | R&D | QAaaS | AUTO | MNGT | Capacité T | MAINT | R&D | QAaaS | AUTO | MNGT | Capacité T | MAINT | R&D | QAaaS | AUTO | MNGT | Capacité T | MAINT | R&D | QAaaS | AUTO | MNGT | Capacité T | MAINT | R&D | QAaaS | AUTO | MNGT | Capacité T | MAINT | R&D | QAaaS | AUTO | MNGT | Capacité T | MAINT | R&D | QAaaS | AUTO | MNGT | Capacité T | MAINT | R&D | QAaaS | AUTO | MNGT | Capacité T | MAINT | R&D | QAaaS | AUTO | MNGT | Capacité T | MAINT | R&D | QAaaS | AUTO | MNGT | Capacité T | MAINT | R&D | QAaaS | AUTO | MNGT
Abir Arrari | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0%
Ahmed Belghith | 80% | 0% | 80% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0%
Alaeddine Boukhriss | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0%
Asma Korbi | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0%
Emna Chaari | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0%
Farah Fenniche | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 0% | 0%
Houssem OUSJI | 100% | 50% | 0% | 50% | 0% | 0% | 100% | 50% | 0% | 50% | 0% | 0% | 100% | 50% | 0% | 50% | 0% | 0% | 100% | 50% | 0% | 50% | 0% | 0% | 100% | 50% | 0% | 50% | 0% | 0% | 100% | 50% | 0% | 50% | 0% | 0% | 100% | 50% | 0% | 50% | 0% | 0% | 100% | 50% | 0% | 50% | 0% | 0% | 100% | 50% | 0% | 50% | 0% | 0% | 100% | 50% | 0% | 50% | 0% | 0% | 100% | 50% | 0% | 50% | 0% | 0% | 100% | 50% | 0% | 50% | 0% | 0% | 100% | 50% | 0% | 50% | 0% | 0%
Ikram Dhraief | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0% | 100% | 0% | 0%
Imen Ben bechir | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 75% | 50% | 0% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Imen BEN SAAD | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0%
Islem LOUATI | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 0% | 25% | 0% | 0% | 0% | 25% | 0% | 25% | 0% | 0% | 0% | 25% | 0% | 25% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25% | 0% | 25% | 0% | 0% | 0% | 25% | 0% | 25% | 0% | 0% | 0% | 25% | 0% | 25% | 0% | 0% | 0% | 25% | 0% | 25% | 0% | 0% | 0% | 25% | 0% | 25% | 0% | 0% | 0% | 25% | 0% | 25% | 0% | 0% | 0%
Khalil Riahi | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0%
Maroua Aissa | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Maryem Tahri | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Monia Dkhil | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Nesrine Dhaouadi | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Oussama MAALEJ | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Ramla Ben Mamya | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Ramy Chaaleb | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0%
Safa Ezzouia | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0% | 100% | 0% | 0% | 0% | 100% | 0%
Sarra BEN GUERGUA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Wafa KALLEL | 25% | 25% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0% | 25% | 25% | 0% | 0% | 0% | 0%
Wassim MALOUCH | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Wieme Abidi | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Yassine SBOUI | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total FTE | 12.05 | 3.75 | 0.8 | 2.5 | 5 | 0 | 12.25 | 3.75 | 1 | 2.5 | 5 | 0 | 12.5 | 3.75 | 1.25 | 2.5 | 5 | 0 | 12.5 | 3.75 | 1.25 | 2.5 | 5 | 0 | 12.5 | 3.75 | 1.25 | 2.5 | 5 | 0 | 13 | 4.25 | 1 | 2.5 | 5.25 | 0 | 12.25 | 3.75 | 1 | 2.5 | 5 | 0 | 12.5 | 3.75 | 1.25 | 2.5 | 5 | 0 | 12.5 | 3.75 | 1.25 | 2.5 | 5 | 0 | 12.5 | 3.75 | 1.25 | 2.5 | 5 | 0 | 12.5 | 3.75 | 1.25 | 2.5 | 5 | 0 | 12.5 | 3.75 | 1.25 | 2.5 | 5 | 0 | 12.5 | 3.75 | 1.25 | 2.5 | 5 | 0

## PARAM
QA | Team | Scope | Etat | Topic
Abir Arrari | Delivery | Automation | In DEV | Maintenance
Ala Eddine Boukhris | Cloud | Cloud | On hold | DH Releases
Molka Gmar | Delivery | Delivery | Ready to TEST | Roadmap
Asma Korbi | Delivery | Roadmap | In TEST | Data@ccess
Ferdews Tlili | Delivery |  | Delivered | Automation
Houssem Ousji | Automation |  | Not Started | Cloud
Ikram Dhraief | Delivery |  |  | Management
Imen Ben Bechir | Delivery |  |  | Absence
Imen Habaieb | Roadmap WEB |  |  | Formation
Islem Louati | Roadmap WEB
Manel Bacha | Automation
Manel Chaabene | Cloud
Maroua Aissa | Roadmap
Monia Dkhil | Automation
Nesrine Dhaouadi | Automation
Oussama Ouledabdallah | Cloud
Ramy Chaaleb | Automation
Rehab Ezzine | Roadmap WEB
Safa Ezzaouia | Automation
Sarra Ben Guerga | Automation
Takwa Jaouadi | Automation
Wafa Kallel | Roadmap
Wassim Malouch | Automation
Wieme Abidi | Delivery
Yassine Sboui | Delivery
Imen Matoussi

## MAINTENANCE old (hidden)
Client | Version | Date CF | Date Livraison | Etat | NB Tickets | Sanity (JH) | Add TC | Charge (JH) | Test ticket | Sanity | Exec TC
GIC | DH-6.3-03c-qf3 | 2023-10-02 | 2023-10-07 | Released | 10 | 0.5 | 15 | 3.3 | 0.25 | 0.5 | 0.02
| DH-6.3-03c-qf4 | 2023-10-02 | 2023-10-07 | Released | 11 | 0.5 | 16 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5
[6 empty] | 0.5 | 15 | 0.5

## Plan de charge QA DH 2024 (hidden)
| Plan de Charge - QA Datahub | [5 empty] | 2024
Scope | Topic | Projet | Version | Etat | QA | Team | Estimé | planifié | Ecart | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01 | 2023-05-08 | 2023-05-15 | 2023-05-22 | 2023-05-29 | 2023-06-05 | 2023-06-12 | 2023-06-19 | 2023-06-26 | 2023-07-03 | 2023-07-10 | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04 | 2023-09-11 | 2023-09-18 | 2023-09-25 | 2023-10-02 | 2023-10-09 | 2023-10-16 | 2023-10-23 | 2023-10-30 | 2023-11-06 | 2023-11-13 | 2023-11-20 | 2023-11-27 | 2023-12-04 | 2023-12-11 | 2023-12-18 | 2023-12-25
[10 empty] | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | S15 | S16 | S17 | S18 | S19 | S20 | S21 | S22 | S23 | S24 | S25 | S26 | S27 | S28 | S29 | S30 | S31 | S32 | S33 | S34 | S35 | S36 | S37 | S38 | S39 | S40 | S41 | S42 | S43 | S44 | S45 | S46 | S47 | S48 | S49 | S50 | S51 | S52
Roadmap | Object Marker | Client lourd |  | On hold | Asma Korbi | Technical |  | 0 | 0
Roadmap | IBOR+ Aggreg | Client lourd |  | In progress | Maryem Tahri | Technical | 15 | 2 | 13 | S1: 2
Roadmap | Scope hiérarchique 14 | Client lourd |  |  | Maryem Tahri | Technical |  | 0 | 0
Roadmap | Merge 3 | Client lourd |  |  | Maryem Tahri | Technical | 2 | 0 | 2
Roadmap | Migration Jenkins? | Client lourd |  |  | Alaeddine Boukhriss | Technical |  | 0 | 0
Roadmap | PnP.CI/CD.Packaging.with.GIT (dev sept - Nov) | Client lourd | [5 empty] | 0 | 0
Roadmap | DataManagement: DQL.Productization & DQC.NewDataModel | Client lourd | [5 empty] | 0 | 0
Roadmap | SellSide (Visage ou Client lourd??) | Client lourd | [5 empty] | 0 | 0
Roadmap | Technical Stack Migration - Java 17 |  | TBD |  |  |  |  | 0 | 0
Roadmap | Technical Stack Migration - Technical.Migration.RMI (Dev Oct - Fev) | [6 empty] | 0 | 0
Roadmap | Technical Stack Migration - Technical.Migration.Serialization (Dev Jan - Apr) | [6 empty] | 0 | 0
Roadmap | Technical Stack Migration - Technical.Security.ZeroVulnerability (dev Nov - Mai) | [6 empty] | 0 | 0
Roadmap | Technical Stack Migration - Architecture.Roadmap.Kafka (dev Oct) | [6 empty] | 0 | 0
Roadmap | Tests Java 11 | [6 empty] | 0 | 0
Roadmap | Cloud | Client lourd |  |  | Ramla Ben Mamya | Technical |  | 0 | 0
Roadmap | Recette Visage | Visage |  |  | Maroua Aissa | Digital |  | 0 | 0
Roadmap |  |  |  |  | Ahmed Belghith | Digital |  | 0
Roadmap |  |  |  |  | Monia Dkhil | Digital |  | 0
Maintenance | Bug fixing & TNR | GIC | DH-6.3-03c-qf3 | Ready to TEST | Asma Korbi |  | 3.3 | 4 | -2.7 | bar: S1 to S4
Maintenance |  |  |  |  | Wieme Abidi |  |  | 2 |  | S2: 2
Maintenance | Autres |  | DH-6.2-02c-qf10 |  |  |  | 0 | 0 | 0
Maintenance | Vanguard Migration - VGD Use case execution | Vanguard | DH-6.2-02c-qf10 |  |  |  | 0 | 0 | 0
Maintenance | Reproduction anciens tickets Majeur (15 tickets) : RAF 5 tickets
Maintenance | Certif Cloud 6.3-04a/Manaos | Manaos |  |  | Ramla Ben Mamya | Technical
QAaaS | POC for GIC | GIC |  |  | Asma Korbi | Technical | 50 | 32 | 18 | S7: 5; S8: 5; S9: 2; S10: 5; S11: 5; S12: 5; S13: 5
Automation | PO et Formalisation | Visage |  |  | Maroua Aissa | Digital |  | 0 | 0
Automation | Test Automation | Visage |  |  | Emna Chaari | Automation |  | 32 | -32 | S7: 5; S8: 5; S9: 2; S10: 5; S11: 5; S12: 5; S13: 5
Automation | Test Automation | Visage |  |  | Imen BEN SAAD | Automation |  | 0 | 0
Automation | Test Automation | Visage |  |  | Khalil Riahi | Automation |  | 32 | -32 | S7: 5; S8: 5; S9: 2; S10: 5; S11: 5; S12: 5; S13: 5
Automation | Test Automation | Visage |  |  | Nesrine Dhaouadi | Automation |  | 0 | 0
Automation | Test Automation | Visage |  |  | Ramy Chaaleb | Automation |  | 32 | -32 | S7: 5; S8: 5; S9: 2; S10: 5; S11: 5; S12: 5; S13: 5
Automation | Test Automation | Visage |  |  | Safa Ezzouia | Automation |  | 0 | 0
Automation | Test Automation | Visage |  |  | Houssem OUSJI | Automation |  | 32 | -32 | S7: 5; S8: 5; S9: 2; S10: 5; S11: 5; S12: 5; S13: 5
Automation | Test Automation | Visage |  |  | Wassim MALOUCH | Automation |  | 0 | 0
Automation | Test Automation | Visage |  |  | Yassine SBOUI | Automation |  | 32 | -32 | S7: 5; S8: 5; S9: 2; S10: 5; S11: 5; S12: 5; S13: 5
QA Improvment | Bitemporal (~ x scenarios) | Refonte TNR |  |  | Asma Korbi |  |  | 0 | 0
QA Improvment |  |  |  |  | Maroua Aissa |  |  | 0
QA Improvment | Bugs migration standard Pictet | Refonte TNR |  |  | Asma Korbi |  |  | 0 | 0
QA Improvment | Data Quality Monitoring & Completness | Refonte TNR |  |  | Asma Korbi |  |  | 0 | 0
QA Improvment | Exception Management | Refonte TNR |  |  | Asma Korbi |  |  | 0 | 0
QA Improvment | Data Selection Policy | Refonte TNR |  |  | Abir Arrari |  |  | 0 | 0
QA Improvment | Raw Data Management (Staging, Extract) | Refonte TNR |  |  | Abir Arrari |  |  | 0 | 0
QA Improvment | Audit & Traceability | Refonte TNR |  |  | Ahmed Belghith |  |  | 0 | 0
QA Improvment | Data Request Manager | Refonte TNR |  |  | Ahmed Belghith |  |  | 0 | 0
QA Improvment | Formater & Parser - JSON | Refonte TNR |  |  | Emna Chaari |  |  | 0 | 0
QA Improvment | Formater & Parser - ISO 15022 (SWIFT) | Refonte TNR |  |  | Ikram Dhraief |  |  | 0 | 0
QA Improvment | Mapping - Triggers | Refonte TNR |  |  | Ikram Dhraief |  |  | 0 | 0
QA Improvment | Detail Screen Configuration | Refonte TNR |  |  | Imen Ben bechir |  |  | 0 | 0
QA Improvment | Navigation & Searching | Refonte TNR |  |  | Imen Ben bechir |  |  | 0 | 0
QA Improvment | Query Screen Configuration | Refonte TNR |  |  | Imen Ben bechir |  |  | 0 | 0
QA Improvment | 4Eyes | Refonte TNR |  |  | Maroua Aissa |  |  | 0 | 0
QA Improvment | Bugs migration standard Vanguard | Refonte TNR |  |  | Maryem Tahri |  |  | 0 | 0
QA Improvment | Aggregation Service | Refonte TNR |  |  | Maryem Tahri |  |  | 0 | 0
QA Improvment | Scope of Interest | Refonte TNR |  |  | Maryem Tahri |  |  | 0 | 0
QA Improvment | Dashboards | Refonte TNR |  |  | Monia Dkhil |  |  | 0 | 0
QA Improvment | Web Grid | Refonte TNR |  |  | Monia Dkhil |  |  | 0 | 0
QA Improvment | Web Navigation & Searching | Refonte TNR |  |  | Monia Dkhil |  |  | 0 | 0
QA Improvment | Formater & Parser - CSV | Refonte TNR |  |  | Nesrine Dhaouadi |  |  | 0 | 0
QA Improvment | Formater & Parser - Excel | Refonte TNR |  |  | Nesrine Dhaouadi |  |  | 0 | 0
QA Improvment | Custom Panels | Refonte TNR |  |  | Ramla Ben Mamya |  |  | 0 | 0
QA Improvment | Web Performance | Refonte TNR |  |  | Ramy Chaaleb |  |  | 0 | 0
QA Improvment | Formater & Parser - XML | Refonte TNR |  |  | Safa Ezzouia |  |  | 0 | 0
QA Improvment | Mapping - Definition | Refonte TNR |  |  | Wieme Abidi |  |  | 0 | 0
QA Improvment | Mapping - Scripts | Refonte TNR |  |  | Wieme Abidi |  |  | 0 | 0
QA Improvment | Mapping - Simulation & Execution | Refonte TNR |  |  | Wieme Abidi |  |  | 0 | 0
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Abir Arrari | Technical |  | 3.5 |  | S3: 1; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Ahmed Belghith | Digital |  | 2.5 |  | S1: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Alaeddine Boukhriss | Technical |  | 4.5 |  | S1: 2; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Asma Korbi | Technical |  | 3.5 |  | S3: 1; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Emna Chaari | Automation |  | 2.5 |  | S1: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Farah Fenniche | Technical |  | 4.5 |  | S1: 2; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Houssem OUSJI | Technical |  | 3.5 |  | S3: 1; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Ikram Dhraief | Technical |  | 2.5 |  | S1: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Imen Ben bechir | Technical |  | 4.5 |  | S1: 2; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Imen BEN SAAD | Automation |  | 3.5 |  | S3: 1; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Islem LOUATI | Technical |  | 2.5 |  | S1: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Khalil Riahi | Automation |  | 4.5 |  | S1: 2; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Maroua Aissa | Digital |  | 3.5 |  | S3: 1; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Maryem Tahri | Technical |  | 2.5 |  | S1: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Monia Dkhil | Digital |  | 4.5 |  | S1: 2; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Nesrine Dhaouadi | Automation |  | 3.5 |  | S3: 1; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Ramla Ben Mamya | Technical |  | 2.5 |  | S1: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Ramy Chaaleb | Automation |  | 4.5 |  | S1: 2; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Safa Ezzouia | Automation |  | 3.5 |  | S3: 1; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Sarra BEN GUERGUA | Automation |  | 2.5 |  | S1: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Wafa KALLEL | Technical |  | 4.5 |  | S1: 2; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Wassim MALOUCH | Automation |  | 3.5 |  | S3: 1; S6: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Wieme Abidi | Technical |  | 2.5 |  | S1: 1; S13: 0.5; S17: 1
Absence | Absence (CP, Maladie, Férié, Etudes universitaires etc.) |  |  |  | Yassine SBOUI | Automation |  | 4.5 |  | S1: 2; S6: 1; S13: 0.5; S17: 1
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Abir Arrari | Technical |  | 3 |  | S4: 1; S6: 2
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Ahmed Belghith | Digital |  | 0
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Alaeddine Boukhriss | Technical |  | 1 | bar: S3
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Asma Korbi | Technical |  | 3 |  | S4: 1; S6: 2
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Emna Chaari | Automation |  | 0
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Farah Fenniche | Technical |  | 1 | bar: S3
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Houssem OUSJI | Technical |  | 3 |  | S4: 1; S6: 2
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Ikram Dhraief | Technical |  | 0
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Imen Ben bechir | Technical |  | 1 | bar: S3
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Imen BEN SAAD | Automation |  | 3 |  | S4: 1; S6: 2
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Islem LOUATI | Technical |  | 0
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Khalil Riahi | Automation |  | 1 | bar: S3
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Maroua Aissa | Digital |  | 3 |  | S4: 1; S6: 2
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Maryem Tahri | Technical |  | 0
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Monia Dkhil | Digital |  | 1 | bar: S3
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Nesrine Dhaouadi | Automation |  | 3 |  | S4: 1; S6: 2
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Ramla Ben Mamya | Technical |  | 0
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Ramy Chaaleb | Automation |  | 1 | bar: S3
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Safa Ezzouia | Automation |  | 3 |  | S4: 1; S6: 2
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Sarra BEN GUERGUA | Automation |  | 0
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Wafa KALLEL | Technical |  | 1 | bar: S3
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Wassim MALOUCH | Automation |  | 3 |  | S4: 1; S6: 2
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Wieme Abidi | Technical |  | 0
Formation | Formation (onboarding, interne, externe, etc.) |  |  |  | Yassine SBOUI | Automation |  | 1 | bar: S3
Total |  |  | Roadmap | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | Maintenance | [6 empty] | 1 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | QAaaS | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | Automation | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | QA Improvment | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total planifié |  |  | QA DH | [6 empty] | 1 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total / Mois |  |  | QA DH | [6 empty] | S1: 6; S5: 0; S9: 0; S14: 0; S18: 0; S22: 0; S27: 0; S31: 0; S36: 0; S40: 0; S44: 0; S49: 0
Nombre de ressources | [9 empty] | 12.05 | 12.25 | 12.5 | 12.5 | 12.5 | 13 | 12.25 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 12.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | Capacité Brute | [6 empty] | 60.25 | 61.25 | 62.5 | 62.5 | 62.5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | Absence | [6 empty] | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | Formation | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | Capacité prod Max | [6 empty] | 36.25 | 61.25 | 62.5 | 62.5 | 62.5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  | Ecart | [6 empty] | 35.25 | 58.25 | 61.5 | 61.5 | 62.5 | 65 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Sujet Roadmap ?
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Scope/ version ? Détails
Note on B24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Il faut bcp plus de détails
Note on B25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Roadmap ou maintenance ?
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Pour quelle version / Client ?
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Roadmap ou maintenance ?

## CAPA QA DH 2024 (hidden)
| 2024-01-01 |  |  | 2024-01-08 |  |  | 2024-01-15 |  |  | 2024-01-22 |  |  | 2024-01-29 |  |  | 2024-02-05 |  |  | 2024-02-12 |  |  | 2024-02-19 |  |  | 2024-02-26 |  |  | 2024-03-04 |  |  | 2024-03-11 |  |  | 2024-03-18 |  |  | 2024-03-25
Ressource | S1 |  |  | S2 |  |  | S3 |  |  | S4 |  |  | S5 |  |  | S6 |  |  | S7 |  |  | S8 |  |  | S9 |  |  | S10 |  |  | S11 |  |  | S12 |  |  | S13
| Capacité E | PRDO | MNGT | Capacité T | PROD | MNGT | Capacité T | PROD | MNGT | Capacité T | PROD | MNGT | Capacité T | PROD | MNGT | Capacité T | PROD | MNGT | Capacité T | PROD | MNGT | Capacité T | PROD | MNGT | Capacité T | PROD | MNGT | Capacité T | PROD | MNGT | Capacité T | PROD | MNGT | Capacité T | PROD | MNGT | Capacité T | PROD | MNGT
Abir Arrari | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0%
Ahmed Belghith | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Alaeddine Boukhriss | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0%
Asma Korbi | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Emna Chaari | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Farah Fenniche | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0% | 100% | 100% | 0%
Houssem OUSJI | 50% | 50% | 0% | 50% | 50% | 0% | 50% | 50% | 0% | 50% | 50% | 0% | 50% | 50% | 0% | 50% | 50% | 0% | 50% | 50% | 0% | 50% | 50% | 0% | 50% | 50% | 0% | 50% | 50% | 0% | 50% | 50% | 0% | 50% | 50% | 0% | 50% | 50% | 0%
Ikram Dhraief | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Imen Ben bechir | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Imen BEN SAAD | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Islem LOUATI | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Khalil Riahi | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Maroua Aissa | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Maryem Tahri | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Monia Dkhil | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Nesrine Dhaouadi | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Oussama MAALEJ | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Ramla Ben Mamya | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Ramy Chaaleb | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Safa Ezzouia | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Sarra BEN GUERGUA | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Wafa KALLEL | 25% | 25% | 0% | 25% | 25% | 0% | 25% | 25% | 0% | 25% | 25% | 0% | 25% | 25% | 0% | 25% | 25% | 0% | 25% | 25% | 0% | 25% | 25% | 0% | 25% | 25% | 0% | 25% | 25% | 0% | 25% | 25% | 0% | 25% | 25% | 0% | 25% | 25% | 0%
Wassim MALOUCH | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Wieme Abidi | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Yassine SBOUI | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
Total FTE | 475% | 475% | 0% | 3.75 | 3.75 | 0 | 3.75 | 3.75 | 0 | 3.75 | 3.75 | 0 | 3.75 | 3.75 | 0 | 4.25 | 4.25 | 0 | 3.75 | 3.75 | 0 | 3.75 | 3.75 | 0 | 3.75 | 3.75 | 0 | 3.75 | 3.75 | 0 | 3.75 | 3.75 | 0 | 3.75 | 3.75 | 0 | 3.75 | 3.75 | 0